## Function Point Calculator
Function Point Estimation
Number | Element (Variable names) | Type | RET/FTR | DET | Complexity
1 | EI-User Log In | EI | 2 | 3 | Low
2 | EQ-System verification | EQ | 2 | 2 | Low
3 | EI-User Logout | EI | 2 | 2 | Low |  |  | COMPLEXITY
4 | EI-User Register | EI | 3 | 2 | Medium |  |  | Simple | Average | Complex | Simple | Average | Complex | Unadjusted FP (UFP)
5 | EO-Look driver profile | EO | 1 | 3 | Low |  | Data Functions | Frequency |  |  | Weighting
6 | EI-Send Message | EI | 4 | 4 | Medium |  | Internal Logical File (ILF) | 1 | 0 | 0 | 7 | 10 | 15 | 7
7 | ILF-User Management | ILF | 1 | 4 | Low |  | External Interface File (EIF) | 1 | 0 | 0 | 5 | 7 | 10 | 5
8 | EIF-System verification | EIF | 1 | 2 | Low |  | Transaction Functions
9 | [6 empty] | External Input (EI) | 2 | 2 | 0 | 3 | 4 | 6 | 14 | 0
10 | [6 empty] | External Output (EO) | 1 | 0 | 0 | 4 | 5 | 7 | 4 | 1
11 | [6 empty] | External Inquiry (EQ) | 1 | 0 | 0 | 3 | 4 | 6 | 3 | 2
12 | [12 empty] | TOTAL | 33 | 3
13 | [14 empty] | 4
14 | [10 empty] | Complexity Factors |  |  | TDI | 5
15 | [6 empty] | Summary |  | Value |  | Data Communications |  |  | 4
16 | [6 empty] | Function Points (FP) |  | 33 |  | Distributed Processing |  |  | 4
17 | [6 empty] | Complexity Adjustment Factor (TDI) |  | 41 |  | Performance |  |  | 3
18 | [6 empty] | Adjustment Factor --> AF = (TDI x 0.01) + 0.65 |  | 1.06 |  | Heavily Used Configuration |  |  | 2
19 | [6 empty] | Adjusted Function Points --> AFP = AF x UFP |  | 34.98 |  | Transaction Rate |  |  | 4
20 | [6 empty] | Work days per Function Point |  | 1.4667 |  | On-line Data Entry |  |  | 5
21 | [6 empty] | Work days |  | 51.304 |  | End-User Efficiency |  |  | 3
22 | [10 empty] | On-line Update |  |  | 3
23 | [10 empty] | Complex Processing |  |  | 0
24 | [10 empty] | Reusability |  |  | 4
25 | [10 empty] | Installation Ease |  |  | 0
26 | [10 empty] | Operational Ease |  |  | 2
27 | [10 empty] | Multiple Sites |  |  | 3
28 | [10 empty] | Facilitate Change |  |  | 4
29 | [10 empty] | TOTAL |  |  | 41
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
ILF
EIF
EI
EO
EQ
ILF & EIF
DET | 0 | 1 | 2 | 3 | 4 | 5 | 6 | RET
1 | Low | Low | Low | Low | Low | Low | Medium
2 | Low | Low | Low | Low | Low | Low | Medium
3 | Low | Low | Low | Low | Low | Low | Medium
4 | Low | Low | Low | Low | Low | Low | Medium
5 | Low | Low | Low | Low | Low | Low | Medium
6 | Low | Low | Low | Low | Low | Low | Medium
7 | Low | Low | Low | Low | Low | Low | Medium
8 | Low | Low | Low | Low | Low | Low | Medium
9 | Low | Low | Low | Low | Low | Low | Medium
10 | Low | Low | Low | Low | Low | Low | Medium
11 | Low | Low | Low | Low | Low | Low | Medium
12 | Low | Low | Low | Low | Low | Low | Medium
13 | Low | Low | Low | Low | Low | Low | Medium
14 | Low | Low | Low | Low | Low | Low | Medium
15 | Low | Low | Low | Low | Low | Low | Medium
16 | Low | Low | Low | Low | Low | Low | Medium
17 | Low | Low | Low | Low | Low | Low | Medium
18 | Low | Low | Low | Low | Low | Low | Medium
19 | Low | Low | Low | Low | Low | Low | Medium
20 | Low | Low | Medium | Medium | Medium | Medium | High
21 | Low | Low | Medium | Medium | Medium | Medium | High
22 | Low | Low | Medium | Medium | Medium | Medium | High
23 | Low | Low | Medium | Medium | Medium | Medium | High
24 | Low | Low | Medium | Medium | Medium | Medium | High
25 | Low | Low | Medium | Medium | Medium | Medium | High
26 | Low | Low | Medium | Medium | Medium | Medium | High
27 | Low | Low | Medium | Medium | Medium | Medium | High
28 | Low | Low | Medium | Medium | Medium | Medium | High
29 | Low | Low | Medium | Medium | Medium | Medium | High
30 | Low | Low | Medium | Medium | Medium | Medium | High
31 | Low | Low | Medium | Medium | Medium | Medium | High
32 | Low | Low | Medium | Medium | Medium | Medium | High
33 | Low | Low | Medium | Medium | Medium | Medium | High
34 | Low | Low | Medium | Medium | Medium | Medium | High
35 | Low | Low | Medium | Medium | Medium | Medium | High
36 | Low | Low | Medium | Medium | Medium | Medium | High
37 | Low | Low | Medium | Medium | Medium | Medium | High
38 | Low | Low | Medium | Medium | Medium | Medium | High
39 | Low | Low | Medium | Medium | Medium | Medium | High
40 | Low | Low | Medium | Medium | Medium | Medium | High
41 | Low | Low | Medium | Medium | Medium | Medium | High
42 | Low | Low | Medium | Medium | Medium | Medium | High
43 | Low | Low | Medium | Medium | Medium | Medium | High
44 | Low | Low | Medium | Medium | Medium | Medium | High
45 | Low | Low | Medium | Medium | Medium | Medium | High
46 | Low | Low | Medium | Medium | Medium | Medium | High
47 | Low | Low | Medium | Medium | Medium | Medium | High
48 | Low | Low | Medium | Medium | Medium | Medium | High
49 | Low | Low | Medium | Medium | Medium | Medium | High
50 | Low | Low | Medium | Medium | Medium | Medium | High
51 | Medium | Medium | High | High | High | High | High
EI
DET | 0 | 1 | 2 | 3 | FTR
1 | Low | Low | Low | Medium
2 | Low | Low | Low | Medium
3 | Low | Low | Low | Medium
4 | Low | Low | Low | Medium
5 | Low | Low | Medium | High
6 | Low | Low | Medium | High
7 | Low | Low | Medium | High
8 | Low | Low | Medium | High
9 | Low | Low | Medium | High
10 | Low | Low | Medium | High
11 | Low | Low | Medium | High
12 | Low | Low | Medium | High
13 | Low | Low | Medium | High
14 | Low | Low | Medium | High
15 | Low | Low | Medium | High
16 | Medium | Medium | High | High
EO and EQ
DET | 0 | 1 | 2 | 3 | 4 | FTR
1 | Low | Low | Low | Low | Medium
2 | Low | Low | Low | Low | Medium
3 | Low | Low | Low | Low | Medium
4 | Low | Low | Low | Low | Medium
5 | Low | Low | Low | Low | Medium
6 | Low | Low | Medium | Medium | High
7 | Low | Low | Medium | Medium | High
8 | Low | Low | Medium | Medium | High
9 | Low | Low | Medium | Medium | High
10 | Low | Low | Medium | Medium | High
11 | Low | Low | Medium | Medium | High
12 | Low | Low | Medium | Medium | High
13 | Low | Low | Medium | Medium | High
14 | Low | Low | Medium | Medium | High
15 | Low | Low | Medium | Medium | High
16 | Low | Low | Medium | Medium | High
17 | Low | Low | Medium | Medium | High
18 | Low | Low | Medium | Medium | High
19 | Low | Low | Medium | Medium | High
20 | Medium | Medium | High | High | High

## Function Point Help
Help to determine Function Point Adjustment Factor Value
Adjustment Factor Value
|  |  |  | 0.65 | 0
1. Data Communications
Data Communications describes the degree to which the application communicates directly with the processor.
The data and control information used in the application are sent or received over communication facilities. Devices connected locally to the control unit are considered to use communication facilities. Protocol is a set of conventions that permit the transfer or exchange of information between two systems or devices. All data communication links require some type of protocol.
|  | Application is pure batch processing or a stand-alone application |  | No influence | 0
2. Distributed Processing
Distributed Data Processing describes the degree to which the application transfers data among physical components of the application.
Distributed data or processing functions are a characteristic of the application within the application boundary.
|  | Data is not transferred or processed on another component of the system. |  | No influence | 0
3. Performance
Performance describes the degree to which response time and throughput performance considerations influenced the application development.
Application performance objectives, stated or approved (or implied) by the user, in either response or throughput, influence (or will influence) the design, development, installation, and support of the application.
|  | No special performance requirements were stated by the user. |  | No influence | 0
4. Heavily Used Configuration
Heavily Used Configuration describes the degree to which computer resource restrictions influenced the development of the application.
A heavily used operational configuration may require special considerations when designing the application. For example, the user wants to run the application on existing or committed equipment that will be heavily used.
|  | No explicit or implicit operational restrictions are included. |  | No influence | 0
5. Transaction Rate
Transaction Rate describes the degree to which the rate of business transactions influenced the development of the application.
The transaction rate is high, and it influences the design, development, installation, and support of the application. Users may require what they regard as normal response time even during times of peak volume.
|  | No peak transaction period is anticipated. |  | No influence | 0
6. Online Data Entry
Online Data Entry describes the degree to which data is entered or retrieved through interactive transactions.
On-line User Interface for data entry, control functions, reports, and queries are provided in the application.
|  | All transactions are processed in batch mode. |  | No influence | 0
7. End-User Efficiency
End-User Efficiency describes the degree of consideration for human factors and ease of use for the user of the application measured.
The on-line functions provided emphasize a design for user efficiency (human factor/user friendliness).
The design includes:
- Navigational aids (e.g., function keys, jumps, dynamically generated menus, hyper-links)
- Menus
- On-line help and documents
- Automated cursor movement
- Scrolling
- Remote printing (via on-line transmissions)
- Pre-assigned function keys (e.g., clear screen, request help, clone screen)
- Batch jobs submitted from on-line transactions
- Drop down List box
- Heavy use of reverse video, highlighting, colors, underlining, and other indicators
- Hard-copy documentation of on-line transactions (e.g., screen print)
- Mouse interface
- Pop-up windows
- Templates and/or defaults
- Bilingual support (supports two languages: count as four items)
- Multi-lingual support (supports more than two languages: count as six items) January
|  | None of the above. |  | No influence | 0
8. Online Update
On-line Update describes the degree to which internal logical files are updated on-line.
The application provides on-line update for the internal logical files.
|  | None. |  | No influence | 0
9. Complex Processing
Complex processing describes the degree to which processing logic influenced the development of the application.
The following components are present:
- Sensitive control and/or application-specific security processing.
- Extensive logical processing
- Extensive mathematical processing
- Much exception processing, resulting in incomplete transactions that must be processed again.
- Complex processing to handle multiple input/output possibilities.
|  | None of the above. |  | No influence | 0
10. Reusability
Reusability describes the degree to which the application and the code in the application have been specifically designed, developed, and supported to be usable in other applications.
|  | No reusable code. |  | No influence | 0
11. Installation Ease
Installation Ease describes the degree to which conversion from previous environments influenced the development of the application.
Conversion and installation ease are characteristics of the application. A conversion and installation plan and/or conversion tools were provided and tested during the system test phase.
|  | No special considerations were stated by the user, and no special setup is required for installation. |  | No influence | 0
12. Operational Ease
Operational Ease describes the degree to which the application attends to operational aspects, such as start-up, back-up, and recovery processes.
Operational ease is a characteristic of the application. The application minimizes the need for manual activities, such as tape mounts, paper handling, and direct on-location manual intervention.
Las facilidades de operación proporcionadas pueden ser las siguientes:
- Start-up, back-up, and recovery processes were provided, but human intervention is required.
- Start-up, back-up, and recovery processes were provided, but no human intervention is required (count as two items)
- The application minimizes the need for tape mounts and/or remote data access requiring human intervention
- The application minimizes the need for paper handling.
|  | No special operational considerations other than the normal back-up procedures were stated by the user. |  | No influence | 0
13. Multiple sites
Multiple Sites describes the degree to which the application has been developed for different hardware and software environments.
|  | The needs of only one installation site were considered in the design. |  | No influence | 0
14. Facilitate Change
Facilitate Change describes the degree to which the application has been developed for easy modification of processing logic or data structure.
The following characteristics can apply for the application:
- Flexible query and report facility is provided that can handle simple requests. (count as 1 item)
- Flexible query and report facility is provided that can handle requests of average complexity. (count as 2 items)
- Flexible query and report facility is provided that can handle complex requests. (count as 3 items)
- Business control data is kept in tables that are maintained by the user with on-line interactive processes, but changes take effect only on the next business cycle. (count as 1 item)
- Business control data is kept in tables that are maintained by the user with on-line interactive processes, and the changes take effect immediately. (count as 2 items)
|  | None of the above. |  | No influence | 0
|  | Influence | Weight
| 0 | No influence | 0
| 1 | Incidental influence | 1
| 2 | Moderate influence | 2
| 3 | Medium influence | 3
| 4 | Significant influence | 4
| 5 | Strong influence | 5
|  | Description |  | Influence
1 |  | Application is pure batch processing or a stand-alone application |  | No influence
|  | Application is batch but has remote data entry or remote printing |  | Incidental influence
|  | Application is batch but has remote data entry and remote printing |  | Moderate influence
|  | Application includes on-line data collection or TP (teleprocessing) front end to a batch process or query system |  | Medium influence
|  | Application is more than a front-end, but supports only one type of TP communications |  | Significant influence
|  | Application is more than a front-end, and supports more than one type of TP communications protocol |  | Strong influence
2 |  | Data is not transferred or processed on another component of the system. |  | No influence
|  | Data is prepared for transfer, then is transferred and processed on another component of the system, for user processing. |  | Incidental influence
|  | Data is prepared for transfer, then is transferred and processed on another component of the system ,not for user processing. |  | Moderate influence
|  | Distributed processing and data transfer are on-line and in one direction only. |  | Medium influence
|  | Distributed processing and data transfer are on-line and in both directions |  | Significant influence
|  | Distributed processing and data transfer are on-line and are dynamically performed on the most appropriate component of the system. |  | Strong influence
3 |  | No special performance requirements were stated by the user. |  | No influence
|  | Performance and design requirements were stated and reviewed but no special actions were required. |  | Incidental influence
|  | Response time or throughput is critical during peak hours. No special design for CPU utilization was required. Processing deadline is for the next business cycle. |  | Moderate influence
|  | Response time or throughput is critical during all business hours. No special design for CPU utilization was required. Processing deadline requirements with interfacing systems are constraining. |  | Medium influence
|  | In addition, stated user performance requirements are stringent enough to require performance analysis tasks in the design phase. |  | Significant influence
|  | In addition, performance analysis tools were used in the design, development, and/or implementation phases to meet the stated user performance requirements. |  | Strong influence
4 |  | No explicit or implicit operational restrictions are included. |  | No influence
|  | Operational restrictions do exist, but are less restrictive than a typical application. No special effort is needed to meet the restrictions. |  | Incidental influence
|  | Stated operational restrictions require special constraints on one piece of the application in the central processor or a dedicated processor. |  | Moderate influence
|  | Stated operational restrictions require special constraints on one piece of the application in the central processor or a dedicated processor. |  | Medium influence
|  | Stated operational restrictions require special constraints on the entire application in the central processor or a dedicated processor. |  | Significant influence
|  | In addition, there are special constraints on the application in the distributed components of the system. |  | Strong influence
5 |  | No peak transaction period is anticipated. |  | No influence
|  | Low transaction rates have minimal effect on the design, development, and installation phases. |  | Incidental influence
|  | Average transaction rates have some effect on the design, development, and installation phases. |  | Moderate influence
|  | High transaction rates affect the design, development, and/or installation phases. |  | Medium influence
|  | High transaction rate(s) stated by the user in the application requirements or service level agreements are high enough to require performance analysis tasks in the design, development, and/or installation phases. |  | Significant influence
|  | High transaction rate(s) stated by the user in the application requirements or service level agreements are high enough to require performance analysis tasks and, in addition, require the use of performance analysis tools in the design, development, and/or installation phases. |  | Strong influence
6 |  | All transactions are processed in batch mode. |  | No influence
|  | 1% to 7% of transactions are interactive. |  | Incidental influence
|  | 8% to 15% of transactions are interactive. |  | Moderate influence
|  | 16% to 23% of transactions are interactive. |  | Medium influence
|  | 24% to 30% of transactions are interactive. |  | Significant influence
|  | More than 30% of transactions are interactive. |  | Strong influence
7 |  | None of the above. |  | No influence
|  | One to three of the above. |  | Incidental influence
|  | Four to five of the above. |  | Moderate influence
|  | Six or more of the above, but there are no specific user requirements related to efficiency. |  | Medium influence
|  | Six or more of the above, and stated requirements for user efficiency are strong enough to require design tasks for human factors to be included. |  | Significant influence
|  | Six or more of the above, and stated requirements for user efficiency are strong enough to require use of special tools and processes in order to demonstrate that the objectives have been achieved. |  | Strong influence
8 |  | None. |  | No influence
|  | On-line update of one to three control files is included. Volume of updating is low and recovery is easy. |  | Incidental influence
|  | On-line update of four or more control files is included. Volume of updating is low and recovery is easy. |  | Moderate influence
|  | On-line update of major internal logical files is included. |  | Medium influence
|  | In addition, protection against data loss is essential and has been specially designed and programmed in the system. |  | Significant influence
|  | In addition, high volumes bring cost considerations into the recovery process. Highly automated recovery procedures with minimum human intervention are included. |  | Strong influence
9 |  | None of the above. |  | No influence
|  | Any one of the above. |  | Incidental influence
|  | Any two of the above. |  | Moderate influence
|  | Any three of the above. |  | Medium influence
|  | Any four of the above. |  | Significant influence
|  | All five of the above. |  | Strong influence
10 |  | No reusable code. |  | No influence
|  | Reusable code is used within the application. |  | Incidental influence
|  | Less than 10% of the application code developed is intended for use in more than one application. |  | Moderate influence
|  | Ten percent (10%) or more of the application code developed is intended for use in more than one application. |  | Medium influence
|  | The application was specifically packaged and/or documented to ease reuse, and the application is customized at the source code level. |  | Significant influence
|  | The application was specifically packaged and/or documented to ease reuse, and the application is customized for use by means of user parameter maintenance. |  | Strong influence
11 |  | No special considerations were stated by the user, and no special setup is required for installation. |  | No influence
|  | No special considerations were stated by the user, but special setup is required for installation. |  | Incidental influence
|  | Conversion and installation requirements were stated by the user, and conversion and installation guides were provided and tested. The impact of conversion on the project is not considered to be important. |  | Moderate influence
|  | Conversion and installation requirements were stated by the user, and conversion and installation guides were provided and tested. The impact of conversion on the project is considered to be important. |  | Medium influence
|  | In addition to 2 above, automated conversion and installation tools were provided and tested. |  | Significant influence
|  | In addition to 3 above, automated conversion and installation tools were provided and tested. |  | Strong influence
12 |  | No special operational considerations other than the normal back-up procedures were stated by the user. |  | No influence
|  | A total of one item from above. |  | Incidental influence
|  | A total of two items from above. |  | Moderate influence
|  | A total of three items from above. |  | Medium influence
|  | A total of four items from above. |  | Significant influence
|  | The application is designed for unattended operation. Unattended operation means no human intervention is required to operate the system other than to start up or shut down the application. Automatic error recovery is a feature of the application. |  | Strong influence
13 |  | The needs of only one installation site were considered in the design. |  | No influence
|  | The needs of more than one installation site were considered in the design, and the application is designed to operate only under identical hardware and software environments. |  | Incidental influence
|  | The needs of more than one installation site were considered in the design, and the application is designed to operate only under similar hardware and/or software environments. |  | Moderate influence
|  | The needs of more than one installation site were considered in the design, and the application is designed to operate under different hardware and/or software environments |  | Medium influence
|  | Documentation and support plan are provided and tested to support the application at multiple installation sites and the application is as described by 2. |  | Significant influence
|  | Documentation and support plan are provided and tested to support the application at multiple installation sites and the application is as described by 3. |  | Strong influence
14 |  | None of the above. |  | No influence
|  | A total of one item from above. |  | Incidental influence
|  | A total of two items from above. |  | Moderate influence
|  | A total of three items from above. |  | Medium influence
|  | A total of four items from above. |  | Significant influence
|  | A total of five items from above. |  | Strong influence